## Slide 1: Information Technology Project Management
By
Denny Ganjar Purnama, MTI
Universitas Pembangunan Jaya
April 2014

## Slide 2: Chapter 7 The Project Schedule and Budget

## Slide 3: Learning Objectives
Describe the Project Management Body of Knowledge (PMBOK®) called Project Cost Management.
Develop a Gantt chart.
Develop a project network diagram using the activity on the node (AON) technique.
Identify a project’s critical path and explain why it must be controlled and managed.
Develop a PERT diagram.
Describe the concept of precedence diagramming and identify finish-to-start, start-to-start, finish-to-finish, and start-to-finish activity relationships.
Describe the various costs for determining the project’s budget.
Define what is meant by the baseline project plan.

## Slide 4: The Project Planning Framework

## Slide 5: PMBOK® Project Cost Management
Resource planning
Cost estimating
Cost budgeting
Cost control

## Slide 7: Schedule Development
Put it all together to determine the start and end dates for the project
Iterations may be necessary
A realistic project schedule is the goal!

## Slide 8: Developing the Project Schedule
Project Management Tools
  Gantt Charts
  Project Network Diagrams
    Activity on the Node (AON)
    Critical Path Analysis
    Program Evaluation and Review Technique (PERT)
    Precedence Diagramming Method (PDM)

## Slide 9: Gantt Chart for Planning

## Slide 10: Gantt Chart Reporting Project’s Progress

## Slide 11: Activity Analysis for AON (Activity On the Node)
Activity | Description | Estimated Duration (Days) | Predecessor
A | Evaluate current technology platform | 2 | None
B | Define user requirements | 5 | A
C | Design Web page layouts | 4 | B
D | Set-up Server | 3 | B
E | Estimate Web traffic | 1 | B
F | Test Web pages and links | 4 | C,D
G | Move web pages to production environment | 3 | D,E
H | Write announcement of intranet for corp. newsletter | 2 | F,G
I | Train users | 5 | G
J | Write report to management | 1 | H,I

## Slide 12: Activity on the Node (AON) Network Diagram

## Slide 13: Possible Activity Paths
Possible Paths | Path | Total
Path 1 | A+B+C+F+H+J | 18
 | 2+5+4+4+2+1 | 
Path 2 | A+B+D+F+H+J | 17
 | 2+5+3+4+2+1 | 
Path 3 | A+B+D+G+H+J | 16
 | 2+5+3+3+2+1 | 
Path 4 | A+B+D+G+I+J | 19*
 | 2+5+3+3+5+1 | 
Path 5 | A+B+E+G+I+J | 17
 | 2+5+1+3+5+1 | 

## Slide 14: Critical Path
Longest path
Shortest time project can be completed
  Zero slack (or float)
    The amount of time an activity can be delayed before it delays the project
Must be monitored and managed!
  Project manager can expedite or crash by adding resources
  Fast tracking – running activities in parallel which were originally planned as sequential
  The CP can change
  Can have multiple CPs

## Slide 15: PERT
Program Evaluation and Review Technique
Developed in 1950s to help manage the Polaris Submarine Project
Developed about the same time as the Critical Path Method
  Often combined as PERT/CPM
Employs both a project network diagram with a statistical distribution

## Slide 16: Activity Analysis for PERT
Activity | Predecessor | Optimistic Estimates (Days) | Most Likely Estimates (Days) | Pessimistic Estimates (Days) | Expected Duration (a+4b+c) 6
A | None | 1 | 2 | 4 | 2.2
B | A | 3 | 5 | 8 | 5.2
C | B | 2 | 4 | 5 | 3.8
D | B | 2 | 3 | 6 | 3.3
E | B | 1 | 1 | 1 | 1.0
F | C,D | 2 | 4 | 6 | 4.0
G | D,E | 2 | 3 | 4 | 3.0
H | F,G | 1 | 2 | 5 | 2.3
I | G | 4 | 5 | 9 | 5.5
J | H,I | .5 | 1 | 3 | 1.3

## Slide 17: Possible PERT Activity Paths
Possible Paths | Path | Total
Path 1 | A+B+C+F+H+J | 18.8
 | 2.2+5.2+3.8+4.0+2.3+1.3 | 
Path 2 | A+B+D+F+H+J | 18.3
 | 2.2+5.2+3.3+4.0+2.3+1.3 | 
Path 3 | A+B+D+G+H+J | 18.6
 | 2.2+5.2+3.3+3.0+2.3+1.3 | 
Path 4 | A+B+D+G+I+J | 20.5*
 | 2.2+5.2+3.3+3.0+5.5+1.3 | 
Path 5 | A+B+E+G+I+J | 18.2
 | 2.2+5.2+1.0+3.0+5.5+1.3 | 

## Slide 18: Precedence Diagramming Method - PDM
Based on 4 fundamental relationships
  Finish-To-Start (FS)
  Start-To-Start (SS)
  Finish-To-Finish (FF)
  Start-To-Finish (SF)

## Slide 19: PDM Relationships

## Slide 20: Lead and Lag times
Lead is starting the next task before the first task is complete
    Example: Begin installing the operating systems when half of the PCs are set up
Lag (or negative lead) is the adding of a buffer of time before the next task begins
    Example: Once the walls have been painted, wait one day before laying the carpet so that the walls have had a chance to dry

## Slide 21: Developing the Project Budget
Define what resources will be needed to perform the work
Determine the quantity of resources that are needed
Define the cost of using each resource
Calculate the cost of the task or activity
Ensure that the resources are leveled, that is, resources have not been over allocated assigned to more than one task scheduled at the same time

## Slide 22: Project Management Software Tools
A number of project management software tools are available to plan and track the progress of your project
However, having a fundamental understanding of these project management techniques is important to make the most of these software tools

## Slide 23: Microsoft Project ® 2003 Gantt Chart View

## Slide 24: Microsoft Project® 2003 PERT Chart View

## Slide 25: Microsoft Project® 2003 Calendar View

## Slide 26: Microsoft Project® 2003 Adding Resources to A Project

## Slide 27: Microsoft Project® 2003 Project Status

## Slide 28: Finalizing the Project Schedule and Budget
The project schedule and budget may require several iterations before it is acceptable to the sponsor, the project manager, and the project team
Once the project schedule and project plan are accepted, the project plan becomes the baseline plan.
Once accepted, the project manager and project team have the authority to execute or carry out the plan.